## Sheet1
COSC1076 ¦ Semester 1 2020
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | Green Dino |  | Progress Classes: | Ahead
Group Member: | Sean Tan |  |  | On-track
Group Member: | Aaron Soa |  |  | Behind
Group Member: | Amy Nguyen |  |  | Way Behind
Tutor: | Dale
Class: | Wed 2:30 pm
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Sean Tan | Aaron Soa | Amy Nguyen
|  |  | Group Formed |  | Weekly Contribution | Completed main menu with "credits" | Completed main menu with "credits" | Completed main menu with "credits"
|  |  | MS Team created |  | Issues | - | - | -
|  |  | Git Repo created |  | Other Notes | - | - | -
Basic Main menu with "credits"
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Sean Tan | Aaron Soa | Amy Nguyen
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | Decided on where to use linkedlist/vector/array, done simple user main menu, contributed to saved-game format | Completed initial design of ADTs, linkedlist implementation, contributed to saved-game format | Completed initial design of ADTs, linkedlist implementation, contributed to saved-game format
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | - | - | -
|  |  | Linked List implementation |  | Other Notes | - | - | -
Simple user prompt for main menu
Contribute to designing lab saved-game format
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution
|  |  | Initialisation of data strctures for new game |  | Issues
|  |  | Implementation(s) or suitable ADTs wrapper for the use of linked-list, vector and arrays, game logic not required |  | Other Notes
ADT implementation for storing information, game loop logic not required
Write Tests Cases for common uses
|  | Progress | Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | User Prompt (for gameplay), but no/minimal error checking |  | Weekly Contribution
|  |  | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic |  | Issues
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
Write more test cases for cases not covered by Week 9 tests
Start Group Written Report
|  | Progress | Way Behind
|  | Week 11 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution
|  |  | Multiple rounds logic & automated scoring |  | Issues
|  |  | Full error checking of user prompt |  | Other Notes
Group Report Written
Final Tests
|  | Progress | On-track