## Sheet1
COSC1076 ¦ Semester 1 2020
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | Green Dino |  | Progress Classes: | Ahead
Group Member: | Sean Tan |  |  | On-track
Group Member: | Aaron Soa |  |  | Behind
Group Member: | Amy Nguyen |  |  | Way Behind
Tutor: | Dale
Class: | Wed 2:30 pm
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Sean Tan | Aaron Soa | Amy Nguyen
|  |  | Group Formed |  | Weekly Contribution | Completed main menu with "credits" | Completed main menu with "credits" | Completed main menu with "credits"
|  |  | MS Team created |  | Issues | - | - | -
|  |  | Git Repo created |  | Other Notes | - | - | -
Basic Main menu with "credits"
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Sean Tan | Aaron Soa | Amy Nguyen
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | Decided on where to use linkedlist/vector/array, done simple user main menu, contributed to saved-game format | Completed initial design of ADTs, linkedlist implementation, contributed to saved-game format | Completed initial design of ADTs, linkedlist implementation, contributed to saved-game format
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | - | - | -
|  |  | Linked List implementation |  | Other Notes | - | - | -
Simple user prompt for main menu
Contribute to designing lab saved-game format
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Sean Tan | Aaron Soa | Amy Nguyen
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Implementation of linked lists, arrays and vectors where suitable. Test cases were used where necessary to test whether certain methods were working or not. Error checking and testing for ADT implementation. | Implementation of arrays and vectors where suitable. Test cases were used where necessary to test whether certain methods were working or not. Save File Format implementation. | Implementation of arrays and vectors where suitable. Test cases were used where necessary to test whether certain methods were working or not. Error checking and testing for ADT implementation. Exception handling for testing.
|  |  | Initialisation of data structures for new game |  | Issues | - | - | -
|  |  | Implementation(s) or suitable ADTs wrapper for the use of linked-list, vector and arrays, game logic not required |  | Other Notes
ADT implementation for storing information, game loop logic not required
Write Tests Cases for common uses
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Sean Tan | Aaron Soa | Amy Nguyen
|  |  | User Prompt (for gameplay), but no/minimal error checking |  | Weekly Contribution | User Prompt for gameplay. Moving tiles from Factory to Players Mosaic. Error Testing and fixing errors. | Implementationg of Load Function continued and updated. Error Testing. | Group Written Report. Implementationg of Save Function continued and updated. Error Testing.
|  |  | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic |  | Issues | - | - | -
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
Write more test cases for cases not covered by Week 9 tests
Start Group Written Report
|  | Progress | On-track
|  | Week 11 | Goals | Tutor Notes | Indidvidual Updates | Sean Tan | Aaron Soa | Amy Nguyen
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Implementation of Game Scoring and User Prompt. Implementation of Player Mosaic continued and updated. Error Testing and fixing errors. Fixed player and game scoring. | Implementationg of Load Function continued and updated. Error Testing and fixing errors. Testing and fixing errors with Load Function. | Group Written Report. Implementationg of Save Function continued and updated. Error Testing and fixing errors. Fixed Wall Tiling (moving tiles to the Wall).
|  |  | Multiple rounds logic & automated scoring |  | Issues | - | - | -
|  |  | Full error checking of user prompt |  | Other Notes
Group Report Written
Final Tests
|  | Progress | On-track